|  |  |
| --- | --- |
| **Month/Meeting(s)** | **Goals/Deliverables** |
| **SEPTEMBER 2019** |
| Commission Meeting Wed, **Sep 11,** 2019 | **DELIVERABLES:** |
| **PMWG Meeting****Wed, Sep 17, 2019**  | 1. IPPS Final/OPPS Proposed Rules 2020- overview and implications
2. CMS quality programs exemption update
3. Total Cost of Care (TCOC) Model update and state goals
4. Hospital quality measurement and incentives: work plan and quality strategy under the TCOC Model
	1. Medicare Performance Adjustment (MPA) update 2022
	2. Readmission Reduction Incentive Program (RRIP) update; subgroup direction 2022
	3. Quality Based Reimbursement (QBR) Program
	4. Maryland Hospital Acquired Conditions (MHAC) Program 2022
	5. Potentially Avoidable Utilization (PAU) per capita metrics 2021
5. Other topics and public comment
 |
| **OCTOBER 2019** |
| Commission MeetingWed, **Oct 16**, 2019 | **DELIVERABLE:**1. Monthly quality update
2. MPA RY 2022 DRAFT RECOMMENDTION
 |
| **PMWG Meeting****Wed, Oct 16, 2019**  | 1. MPA RY 2022 Quality Update discussion
2. QBR RY 2022 DRAFT policy discussion
3. MHAC RY 2022 updates discussion
4. RRIP RY 2022 re-design updates discussion
 |
| **NOVEMBER 2019** |
| Commission MeetingMon, **Nov 13**, 2019 | **DELIVERABLES**1. Monthly quality update
2. MPA Quality Update RY 2022 FINAL RECOMMENDATION
3. QBR RY 2022 DRAFT RECOMMENDATION
 |
| **PMWG Meeting****Wed, Nov 20, 2019** | 1. QBR RY 2022 FINAL Policy discussion
2. MHAC RY 2022 DRAFT policy discussion
3. RRIP RY 2022 updates discussion
4. PAU RY 2021 updates discussion
5. TCOC Model hospital population health goals update
 |
| **DECEMBER 2019** |
| Commission Meeting Wed, Dec 11, 2019 | **DELIVERABLES**1. Quality update
2. QBR RY 2022 FINAL POLICY RECOMMENDSATION
3. MHAC RY 2022 DRAFT POLICY RECOMMENDATION
 |
| **PMWG Meeting****Wed, Dec 18, 2019** | 1. MHAC RY 2022 Final Policy discussion
2. RRIP RY 2022 draft policy discussion
3. PAU RY 2021 updates discussion
4. TCOC Model hospital population health goals, ongoing
5. Other items TBD
 |
| **JANUARY 2020** |
| Commission Meeting January 2020 | **DELIVERABLES**1. Monthly quality update
2. MHAC RY 2022 FINAL RECOMMENDATION
3. PAU Savings RY 2021-22 Measures Report
 |
| **PMWG Meeting****Wed, Jan 15, 2020** | 1. RRIP RY 2022 draft policy discussion
2. Mortality measure for RY 2021 - TBD
3. TCOC Model hospital population health goals, ongoing
4. Other items TBD
 |
| **FEBRUARY 2020** |
| Commission Meeting February 2020 | **DELIVERABLES**1. Quality Update
2. RRIP RY 2022 DRAFT RECOMMENDATION
 |
| **PMWG Meeting****Wed, Feb 19, 2020**  | 1. RRIP RY 2022 Final Policy discussion
2. QBR RY 2023 redesign
3. TCOC Model Measurement Strategy Discussion
 |
| **MARCH 2020** |
| Commission MeetingMarch 2020 | **DELIVERABLES**1. Monthly Quality Update
2. RRIP RY 2022 FINAL RECOMMENDATION
 |
| **PMWG Meeting****Wed, Mar 18, 2020** | 1. TCOC Model Measurement Strategy Discussion
	1. Outcomes Based Credits update
2. Maternal health quality discussion
3. PAU Savings RY 2021 policy for update factor
 |
| **APRIL 2020** |
| Commission Meeting April 2020 | 1. Monthly Quality Update
 |
|  **PMWG Meeting****Wed, Apr 15, 2020** | 1. Future PAU Savings measures
2. TCOC Model Measurement Strategy Discussion
3. Maternal health quality discussion
4. Revenue at Risk for quality compared to the nation
 |
| **MAY 2020** |
| Commission Meeting May 2020 | **DELIVERABLES**1. Monthly Quality Update
2. PAU Savings RY 2021 (in draft Update Factor Policy)
 |
| **PMWG Meeting****Wed, May 20, 2020** | 1. PAU Savings
	1. PAU Savings RY 2021 in Update Factor Policy
	2. Future PAU Savings measures
2. TCOC Model Measurement Strategy Discussion
3. Other items TBD
 |

\*Topics and timeline may be added or modified based on strategic priorities.