HSCRC Performance Measurement Workgroup

Work Plan

Updated 4/1/14

| Meeting Date | Meeting Goals |
| --- | --- |
| February 6 1:00-3:30 MHA Conference Center | - Review workgroup charge and draft schedule - Discuss State Model Quality Targets and general approach for quality improvement |
| February 20 1:00-3:30 MHA Conference Center | Discuss State Quality Targets for CY 2014 and future policy change options, including introduction of: - Readmission targets - New potentially preventable complication model options - Potentially avoidable utilization (synthesis of white papers) |
| February 28 1:00-3:30 HSCRC | - Finalize hospital performance measurement policy and recommendations for reaching potentially preventable complication targets for FY 2016 - Finalize measurement of readmissions and readmission targets for FY 2016 - Discuss next steps on potentially avoidable utilization measurement and monitoring |
| February Deliverables | For Calendar Year 2014 Measurement Period: - Potentially Preventable Complication Measures and Policy - Readmission Measurement Policy |
| April 2 1:00-4:00 HSCRC | - Review performance monitoring measures under new Model - Discuss efficiency and cost measures, including framework and issues (Discern) - HSCRC cost measures |
| April 24 9:00-12:00 HSCRC | - Discuss strategy for patient-centered, population-based measurement, including: - Vision - Measure domains/measures—available measures and gaps (Johns Hopkins and Discern) - Phasing - Discuss balanced scorecard constructs to measure system/hospital performance |
| May 9 1:00-4:00 HSCRC | - Discuss plan to develop balanced scorecard to measure system/hospital performance with 10 indicators - Review measures for ambulatory care settings (Discern) |
| May Deliverable | Report on Efficiency/Cost Measures for CY 2014 |
| May 28 1:00-4:00 HSCRC | - Finalize strategy for population-based, patient centered measurement, including phased implementation plan and balanced scorecard - Discuss options for combining measures of cost, quality, and health; potential NQF presentation on their related work. |
| May Deliverable | Draft Report on Patient-Centered, Population-Based Performance Measurement and Value-Based Payment Vision and Strategy |
| June 20 1:00-4:00 HSCRC | - Review draft report and discuss remaining issues - Discuss plan for filling gaps in available measures - Revisit measures of potentially avoidable utilization |
| Late June | Finalize report |
| July Deliverable | Final Report on Patient-Centered, Population-Based Performance Measurement and Value-Based Payment Vision and Strategy, including Balanced Scorecard |

Note:  This work plan is subject to change.  Meetings or conference calls could be added, or some materials may be reviewed via email.