## Slide 1: Emergency Department Wait Time Reduction Commission
October 3rd, 2025

## Slide 2: Agenda
AHEAD Update - Jon Kromm
Subgroup Updates - Tina Simmons
ED Hospital Modeling Update - Geoff Dougherty
Legislative Report Discussion - All
Open Forum - All Commissioners
Next Steps - Tina Simmons

## Slide 3: AHEAD Update

## Slide 4: Subgroup Updates

## Slide 5: Commission Subcommittees
Hospital Capacity, Operations & Staffing
Access to Non-Hospital Care
Data Subcommittee
ED-Hospital Best Practices
Integrate and optimize non-hospital care.
Priority Focus:
                Post-acute access, capacity, and function
                Palliative Care/Hospice Care
                Action Items/Deliverables:
Proposal & Recommendations to Regulatory Agencies and Legislature
Expansion of Palliative Care & Hospice Care Training, Resources, and Monitoring
Priority Focus:
Identify existing and develop new data reports that can be used to identify and quantify opportunities across the continuum of care.
Action Items/Deliverables:
Develop a model that quantifies impact of interventions on capacity, throughput and operations that impact Inpatient and ED LOS
Support data analytical work of all subgroups
Priority Focus:
Development of best practices that will improve hospital and ED throughput and decrease ED LOS
To provides input into the methodology for ED-related pay for performance metrics
Action Items/ Deliverables:
Minimum of Two Best Practices implemented at each hospital
Refine Quality Based Reimbursement (QBR) ED LOS methodology, specifically targets, risk adjustment, exclusions.
Priority Focus:
Recommendations for improvement opportunities related to capacity, operations and workforce across the continuum of care.
Action Items/Deliverables: (Pending finalization)
Baseline Capacity analysis
Capacity calculator with standard targets
Recommendations for alternate capacity types (ex. HAH)

## Slide 6: Subgroup Updates
Capacity, Operations & Staffing Subgroup
  Next meeting is 10/21, will discuss:
    Moving forward with acute and post-acute capacity analysis work
    Inpatient LOS opportunities
Access to Non-Hospital Care Subgroup
  10/2 meeting cancelled due to Yom Kippur
    Propose inviting some access to non-hospital care subgroup members to participate in the post-acute capacity discussion at the 10/21 Capacity, Operations & Staffing meeting
Best Practices Subgroup
  Draft Recommendations for CY 2026 Best Practice Policy will go to 10/8 HSCRC Commission meeting.
  Recommendation is to continue the monitoring phase of the Best Practice measures to ensure adequate time to understand the impact of each best practice at individual hospitals and across the state, as well as determine how this program will be integrated into and align with the AHEAD model transition.
Data Subgroup
  ED LOS Dashboard in development; anticipate final draft in November
  ED Hospital Modeling work continues; see next slides for additional updates

## Slide 7: ED Hospital Modeling Update

## Slide 8: Project timeline
Task | Target Date
Work through feedback from modeling group, confirm validity using historical data | 10/2025
Evaluate short list of high-priority interventions using model, present to ED Commission | 11/25
Determine whether evaluation of additional interventions is necessary. | 11/25
Consider model expansion to postacute/primary care, etc. | TBD

## Slide 9: How will we know if the model is valid?
Does the model reproduce historical data on ED-1 and OP-18?
Does the model reproduce historical data on other important ED dynamics?
ED volume by hour | Number of patients in waiting room
Percentage of patients admitted | Number of patients in treatment
Boarding time | IP occupancy
Percentage of patients LWBS | IP length of stay
Time to initial provider contact | Time with physician
Time to disposition | Time with nurse
Time to discharge | Percentage of patients transferred

## Slide 10: Initial interventions to test
Intervention | Effect on Model Inputs
Improved SNF prior authorization | Reduces variability in IP LOS and/or mean IP LOS
Expanded IP discharge window | Allow patients to leave 24/7, increasing IP capacity
Prioritizing IP bed availability for ED patients | Increased variability in direct admit volume
ED budget increase | Increased RN/MD staffing

## Slide 11: Legislative Report

## Slide 12: Legislative Report Timeline
By November 1, 2025 the Commission must report to the Governor and the General Assembly on:
  Year 1 Commission activities, findings, and recommendations
Draft will be sent to MDH next week for review and edits
Final Draft will be sent to the Governor’s office for review prior to November 1st submission to the General Assembly.

## Slide 13: Legislative Report Feedback from Commissioners
Provide high level updates on the ongoing work related to primary care (increasing access), behavioral health and pediatric overstays being led by MDH and other commissions
  Will request MDH team add high-level updates on three areas identified
  Can we clarify that the goal of “ensuring patients are seen in the most appropriate setting” is work that will be driven by MDH and other external commissions and supported by this commission, but is not directly in scope for this commission?
  Add language to explain why primary care/specialty care were prioritized below post-acute care (provide more details on work being done by other agencies, as well as utilization improvements seen with Maryland’s investments in primary care)
Add a data table in the background section that shows volumes and % admitted patients through ED–will be added today
Provide additional high-level detail on palliative care and advance directives opportunities including opportunities to partner with other organizations (pg.8), highlight work being done by MDH on advance directives

## Slide 14: Legislative Report Feedback from Commissioners Continued
Highlight staffing as a priority for the capacity, operations and staffing subgroup in year 2, as staffing opportunities are not discussed in detail in the interim draft
  Evaluate opportunity in year 2 to perform a review of specialty-specific workforce bottlenecks and shortages (physicians, nurses, and other staff); also explore opportunities to engage with other workgroups focused on staffing
Clarify whether the post-acute SNF authorization issues mentioned in the draft will be in scope or out of scope of this commission
  Will we advise on the issue and support the work of other agencies or will be take the lead in making a recommendation?
Opportunity to enhance the consistency of the stated focus of access to non-hospital care subgroup throughout the document
Review tone of discussion regarding impact of academic medical centers on ED Wait Time to ensure our statements don’t create a negative connotation
Several tone, tense, and active voice wording edits suggested and implemented

## Slide 15: Addition to Post Acute Resource Gap Data-Please Review
Post-Acute Resource Gaps: Maryland faces a relative shortage of SNF beds compared to other states. This makes it harder to discharge patients who no longer need acute care, leading to bottlenecks on IP units and longer waits for ED patients needing admission. According to the Nursing Home Compare Data released in July 2025, Maryland is ranked 30th in the country for post-acute bed capacity, requiring 1,688 additional SNF beds to meet national average. The HSCRC also performed an analysis using Kaiser and census data to evaluate how post-acute beds in Maryland compared to the US national average, as well as Connecticut as a peer state. In addition, the analysis evaluated Maryland and DC combined since there is a significant sharing of patients across the Maryland and DC borders. The results indicate a shortage of 1600 SNF in Maryland compared to the national average, which is inline with the 2025 Nursing Home Compare Data cited above. When compared to Connecticut, Maryland has 15,300 fewer SNF beds. Looking at Maryland and DC combined, 2400 SNF beds would be needed to be equivalent to the national average and 17, 600 beds would be needed to be equivalent to the peer state of Connecticut. (Need source to cite)

## Slide 16: Open Forum

## Slide 17: Next Steps
Next Meeting: December 3, 11AM-1PM (Tentative)
Please visit the ED Wait Time Reduction Commission Webpage for all materials.

## Slide 18: Links
https://doi.org/10.1016/j.hjdsi.2025.100769
https://www.medscape.com/viewarticle/children-mental-health-crisis-dont-need-these-tests-are-2025a1000o7c?ecd=wnl_dne8_250915_MSCPEDIT_etid7720417&uac=4882MN&impID=7720417
https://www.jointcommissionjournal.com/article/S1553-7250(25)00138-2/abstract
https://www.beckershospitalreview.com/quality/patient-safety-outcomes/ed-wait-times-keep-going-up-7-notes/?origin=BHRE&utm_source=BHRE&utm_medium=email&utm_content=newsletter&oly_enc_id=3013B3483078A2X
https://www.beckershospitalreview.com/rankings-and-ratings/ed-visits-per-1000-population-by-state/?origin=BHRSUN&utm_source=BHRSUN&utm_medium=email&utm_content=newsletter&oly_enc_id=3013B3483078A2X