## ALL Strategies
Key |  | In Progress
Complete
| Red Text | Critical
Responsible Parties:
Regional Partnership Project Manager- Coordination, Facilitation, Coaching and Oversight
Activity | Hospital
Community Partner Engagement (Involves all Strategies and Work Teams) |  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Education and Training | FRHS
MMC
WMHS
In Progress
Complete
| Red Text | 2016-01-01: Critical
Provider Engagement (Involves all Strategies and Work Teams) |  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Education and Training | FMH
MMC
WMHS
Regional Partnership (Will involve Project Manager, Work Team Leads, and Executive Committee) |  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Create performance dashboards for each strategy | bar: 2016-01-01 to 2016-03-01
Performance measurement of utilization reduction | bar: 2016-01-01 to 2016-03-01
Performance measurement of readmissions | bar: 2016-01-01 to 2016-03-01
Performance measurement of cost avoidance | bar: 2016-01-01 to 2016-03-01
Performance measurement of PQI reduction | bar: 2016-01-01 to 2016-03-01
Refine patient satisfaction metrics | bar: 2016-01-01 to 2016-03-01
Determine standard method for tracking and reporting patient satisfaction metric at each hospital | bar: 2016-01-01 to 2016-03-01
Define and standardize metric reporting processes at the following levels: departmental, hospital and regional levels as per needed time frames as specified by each needed metric | bar: 2016-01-01 to 2016-03-01
Develop and deploy flagging mechanism for each strategies HU target populations that can be rapidly deployed | bar: 2016-01-01 to 2016-03-01
Develop Electronic Health Record capabilities to allow for more timely recongition of HU's that meet, and no longer meet, inclusion criteria.
Recuritement and Hiring- (All Strategies Combined- see Strategy specific Tabs for Details/Strategy) | bar: 2016-01-01 to 2016-07-01
Training (All Stratgies Combined- see Strategy specific Tabs for Details/Strategy) | bar: 2016-01-01 to 2016-10-01
Revsions/Creation and Approval of Job Descriptions for Needed Positions (All Strategies) | bar: 2016-01-01
In Progress
Complete
| Red Text | 2016-01-01: Critical
Reporting and Oversight (Project Manager will facilitate and coordinate; will involve Work Team Leads and Exec. Committee) |  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Progress oversight at Executive Committee (Bimonthly at first, then monthly)
Build of Enabling Infrastructure: |  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Hiring of Project Coordinator | bar: 2016-01-01 to 2016-03-01
Training of Project Coordinator | bar: 2016-04-01 to 2016-06-01
Hiring of Staff Accountant | bar: 2016-01-01 to 2016-03-01
Training of Staff Accountant | bar: 2016-04-01 to 2016-06-01
Hiring of 3 Managers to support additional staff at each Hospital | bar: 2016-01-01 to 2016-04-01
Training of 3 Managers to support additional staff at each Hospital | bar: 2016-04-01 to 2016-07-01

## Strategy 1 BH
Key |  | In Progress
Complete
Barrier
Responsible Parites:
Strategy 1- Work Team Leads
Activity | Hospital | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Behavioral Health Case Management : | All
Create Regional Behavioral Health Case Mgr job description and scope
Hire / re-deploy Regional BH Case Managers
Develop BH CM training content
Develop standardized documentation
Develop reporting system for tracking outcomes
Training and orientation of staff
Deploy staff to begin seeing all BH patients referred from acute care services
Conduct 30 day review with new hires
Conduct 90 day review with new hires
Tracking and documentation using standard form
Evaluate metrics quarterly
Determine patient satisfaction metric
Determine standard method for trackign and reporting physician satisfaction metric
In Progress
Complete
Barrier
Behavioral Health Integration in Primary Care | All | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Create Regional Masters licensed BH clinician job description and scope
Hire / re-deploy Masters licensed BH clinicians for primary care practices
Develop BH CM training content
Develop standardized documentation
Develop reporting system for tracking outcomes
Define and implement method to track PHQ 2 and PHQ 9 results
Work with IT to buld reports to break results down into: 1-4, 5-9 (at risk), 9-14 (moderate), 15-19 (moderately sever, 20-27 (severe)
Clarify scope of service for BH clinician located in PCP office
Partner with PCP providers and practice managers
Training and orientation of staff
Conduct 30 day review with new hires
Deploy staff to begin seeing BH patients referred by PCP
Develop provider training for PHQ2/9
Provide PHQ 2/9 education to PCP team
Conduct 90 day review with new hires
Evaluate PCP office processes and implement use of PHQ 2/9
Tracking and documentation using standard form
BH clinicians begin seeing BH patients referred by PCP using PHQ 9 scoring
In Progress
Complete
Barrier
Reduce Stigma and Increase Understanding of Behavioral Health |  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Create Regional Health Education Coor. job description and scope | bar: 2016-01-01
Recruit and hire a regional community health education coordinator | bar: 2016-01-01 to 2016-03-01
Coordinator obtain MHFA certification | bar: 2016-04-01
Inventory existing MHFA and other training to targeted groups | bar: 2016-01-01 to 2016-04-01
With CAC-develop a training plan-including partners, schedule, logistics. | bar: 2016-04-01 to 2016-05-01
Implement community health education/MHFA throughout region. | bar: 2016-05-01 to 2016-12-01
Create needed materials to increase awareness of behavioral health needs, including zone cards. | bar: 2016-03-01 to 2016-07-01
Distribute consistent education with partners to support appropriate resource utilization. | bar: 2016-07-01 to 2016-12-01
Gather training data by audience type and ED metric. | bar: 2016-05-01 to 2016-12-01
Collaborate with partners to insure availability of certified instructors

## Strategy 2 CCM
Key |  | In Progress
Complete
| Red Text | Critical
Responsible Parties:
Strategy 2- Work Team Leads
Activity | Hospital | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Regional Education Center | All
Create CM Education Specialist Job Duties and Scope
Create Regional Coordinator Job Duties and Scope
Create Regional Education Community Partner Liasion Job Duties and Scope
Hire CM Education Specialist
Hire Regional Coordinator
Hire Regional Education Community Partner Liasion
Train CM Education Specialist
Develop CHW Training content
Create Training Schedule for CHW
Develop CM survey for eductional gaps
Administer the annual CM survey for educational gaps
Survey community care management partners of educational needs
Infrastructure Build Out
Implement Compass Training for current Staff
Implement Compass Training for new staff
Build Health Coach Training
In Progress
Complete
Barrier
Introduction/Expansion of Complex Care Models at FRHS | FRHS | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Hire RN CM
Hire Community Health Workers
Hire RN for Clinic
Hire NP
Hire Receptionist
Hire Respiratory Therapist
Hire Registered Dietician
Hire Social Work Care Manager
Train CHW staff
Train RN CM
Train RN for Clinic
Train NP
Train Receptionist
Train Respiratory Therapist
Train Registered Dietician
Train Social Work Care Manager
In Progress
Complete
Barrier
Introduction/Expansion of Complex Care Models at MMC | MMC | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Hire Community Health Workers (9)
Hire RN Care Manager (1)
Hire Respiratory Therapist (1)
Hire Registered Dietician (2)
Hire Social Work Care Manager (3)
Hire Pharmacists (2.2)
Develop Registered Dietician service line and scope of work
Train CHW staff (9)
Train RN Care Manager (1)
Train Respiratory Therapist (1)
Train Registered Dietician (2)
Train Social Work Care Manager (3)
Train Pharmacists (2.2)
In Progress
Complete
Barrier
Introduction/Expansion of Complex Care Models at WMHS | WMHS | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Hire NP (2)
Hire Medical Assistant/Registrar (1)
Hire Community Health Workers (2)
Hire RN CM (2)
Hire Registered Dietician (1)
Hire Pharmacists (1)
Hire Social Work Care Managers (1)
Train NP (2)
Train Medical Assistant/Registrar (1)
Train Community Health Workers (2)
Train RN CM (2)
Train Registered Dietician (1)
Train Pharmacist (1)
Train Social Work Care Managers (1)
Community Health Workers | All | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Alliance Hiring of CHW- TBD
Alliance Training of CHW
Alliance Purchasing and Outfiting with IT items
CHW Tool (Care at Hand) - Selection, contracting, implementation

## WT2 notes (hidden)
Coumadin Clinic |  | Jan-Mar 2016 | Apri- June | July-Sept | Oct-Dec | Jan-March
Clinic Start Up Time: | awaiting how long took WMHS to start-up
Figure out how to get as close to 100% of all patients discharged from hospital on anticoag medication referred to clinic. | year 1 p rph hired
? How long takes to achieve RX certifcation/onboarding- (CACP- 2yrs exp & 700hrs training);WMHS had seen >800 pt's within the first 5 mos.(need to ask Carrie when believe could fill position)
Rx Protocol Development for Coumadin Clinic dosing (pharmacy has protocol- MD pharmacist collaborative practice)
Define follow up w PCP regarding dose changes (WMHS has process)
Increase the # of outpatients put on anticoagmedication referred to clinic. | year 1 p rph hired
Education regarding clinic w/PCP and Cardiologist |  | X | x | x | x | x
Need referral process established (Electronic/Automated)
Determine what pe4rcentage we have now of these 2 groups at FMH and WMHS so we can figure out how many more pharmacists and MA/Phelbotomist we need | to gain info tomorrow after M. Cague runs FMH AC clinic info.
Combination of policies (could be worked on pre-grant)
Develop policy via MEC from all 3 hospitals to support this | 3
Reduction in how much
What is or are the metrics to monitor
What are we already doing in any areas that can be supported by the grant to inhnce our effectivenes in reducing admission and readmissions that will not require a long lead time in education
At WMHS adding Transition Clinic
At FMH-
At Meritus-
Cost of staff to do this
Reduction in how much
What is or are the metrics to monitor
Education time line
Who are we going to educate
What is the time line
What is the cost
When will they start making an impact in reducing admissions and readmissions
What is or are the metrics to monitor
I think we need to do the same thing for every position we are talkiang about additng for each of the 3 groups
Streamline training CM
Proposed Staffing | Recruitement | Onboarding | FMH | MMC | WMHS
CHW Staffing - 1:50 Ratio |  |  | 9 | 9 | 5
RN CM - 1:125 Ratio | 3 MOS | 3 WEEKS | 2 |  | 2
RN | 3 MOS | 3 WEEKS |  |  | 1
Pharmacist (Jackie and Heather need ID where come from and budget time to mobilize) |  |  |  | 2.2
Phlebotomist |  |  |  | 1
Nurse Practitioner |  |  | 2 | 1 | 2
Receptionist |  |  |  |  | 1
Dietician | 2MOS | 3 WEEKS |  | 1
CM Ed Specialist |  |  | 1
Education Center Coordinator |  |  | 1
Community Partner Liasion |  |  | 1
Technology Needs:
First year
Second year

## Strategy 3 ED PAU
Key |  | In Progress
Complete
| Red Text | Critical
Responsible Parties:
Strategy 3- Work Team Lead
Activity | Hospital | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Paramedicine Staffing/support | FRHS
Partern with community EMS re. development of program
MEIMMS approval to implement
Recruitment of staff
Training and orientation
Deploy resources
Tracking and documentation using standard form
Evaluate metrics quarterly
MMC
Partern with community EMS re. development of program
MEIMMS approval to implement
Recruitment of staff
Training and orientation
Deploy resources
Tracking and documentation using standard form
Evaluate metrics quarterly
WMHS
Partern with community EMS re. development of program
MEIMMS approval to implement
Recruitment of staff
Training and orientation
Deploy resources
Tracking and documentation using standard form
Evaluate metrics quarterly
In Progress
Complete
Barrier
| Hospital | [11 empty] | 2016-12-01
|  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01
Community Health Worker | FRHS
Recruitment of staff
Training and orientation | bar: 2016-03-01 to 2016-11-01
Deploy resources | bar: 2016-03-01 to 2016-11-01
Tracking and documentation using standard form | bar: 2016-04-01 to 2016-11-01
Evaluate metrics quarterly
MMC
Recruitment of staff
Training and orientation | bar: 2016-03-01 to 2016-11-01
Deploy resources | bar: 2016-03-01 to 2016-11-01
Tracking and documentation using standard form | bar: 2016-04-01 to 2016-11-01
Evaluate metrics quarterly
WMHS
Recruitment of staff
Training and orientation | bar: 2016-03-01 to 2016-11-01
Deploy resources | bar: 2016-03-01 to 2016-11-01
Tracking and documentation using standard form | bar: 2016-04-01 to 2016-11-01
Evaluate metrics quarterly
In Progress
Complete
Barrier
| Hospital | [11 empty] | 2016-12-01
|  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01
Regional Partnership - Telemonitoring strategy | FRHS
Select and contract w/vendor of choice
Training and eduction of staff | bar: 2016-03-01 to 2016-11-01
Deployment of patient monitoring system | bar: 2016-03-01 to 2016-11-01
Tracking and documentation using standard form | bar: 2016-04-01 to 2016-11-01
Evaluate metrics quarterly | bar: 2016-07-01 to 2016-11-01
MMC
Select and contract w/vendor of choice
Training and eduction of staff | bar: 2016-03-01 to 2016-11-01
Deployment of patient monitoring system | bar: 2016-03-01 to 2016-11-01
Tracking and documentation using standard form | bar: 2016-04-01 to 2016-11-01
Evaluate metrics quarterly | bar: 2016-07-01 to 2016-11-01
WMHS
Select and contract w/vendor of choice
Training and eduction of staff | bar: 2016-03-01 to 2016-11-01
Deployment of patient monitoring system | bar: 2016-03-01 to 2016-11-01
Tracking and documentation using standard form | bar: 2016-04-01 to 2016-11-01
Evaluate metrics quarterly | bar: 2016-07-01 to 2016-11-01
In Progress
Complete
Barrier
2016-12-01
| Hospital | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01
Regional Partnership Implementation of Secure Texting | FRHS
Select and contract w/vendor of choice | bar: 2016-01-01
Training and eduction of staff/physicians and other providers
Evaluate metrics quarterly | bar: 2016-04-01 to 2016-11-01
MMC | bar: 2016-01-01
Select and contract w/vendor of choice
Training and eduction of staff/physicians and other providers | bar: 2016-04-01 to 2016-11-01
Evaluate metrics quarterly
WMHS | bar: 2016-01-01
Select and contract w/vendor of choice
Training and eduction of staff/physicians and other providers | bar: 2016-04-01 to 2016-11-01
Evaluate metrics quarterly
TBD after baseline "need" identified and strategies for implementation reviewed
In Progress
Complete
Barrier
2016-12-01
| Hospital | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01
Centralized Call Center | FRHS
Identify and implement technology to support Center activities
Define roles and responsibilities
Create workflows and accountabilities
Recruit staff | bar: 2016-03-01 to 2016-11-01
Training and orientation | bar: 2016-03-01 to 2016-11-01
Deploy resources | bar: 2016-03-01 to 2016-11-01
Tracking and documentation using standard form | bar: 2016-08-01 to 2016-11-01
Evaluate metrics quarterly
MMC
Identify and implement technology to support Center activities
Define roles and responsibilities
Create workflows and accountabilities
Recruit staff
Training and orientation | bar: 2016-03-01 to 2016-11-01
Deploy resources | bar: 2016-03-01 to 2016-11-01
Tracking and documentation using standard form | bar: 2016-03-01 to 2016-11-01
Evaluate metrics quarterly | bar: 2016-08-01 to 2016-11-01
WMHS
Identify and implement technology to support Center activities
Define roles and responsibilities
Create workflows and accountabilities
Recruit staff
Training and orientation | bar: 2016-03-01 to 2016-11-01
Deploy resources | bar: 2016-03-01 to 2016-11-01
Tracking and documentation using standard form | bar: 2016-03-01 to 2016-11-01
Evaluate metrics quarterly | bar: 2016-08-01 to 2016-11-01

## Strategy 4- RCMEC
Key |  | In Progress
Complete
| Red Text | Critical
Responsible Parties:
Strategy 2- Work Team Leads
Activity | Hospital | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
Regional Education Center | All
Create CM Education Specialist Job Duties and Scope
Create Regional Coordinator Job Duties and Scope
Create Regional Education Community Partner Liasion Job Duties and Scope
Hire CM Education Specialist
Hire Regional Coordinator
Hire Regional Education Community Partner Liasion
Train CM Education Specialist
Develop CHW Training content
Create Training Schedule for CHW
Develop CM survey for eductional gaps
Administer the annual CM survey for educational gaps
Survey community care management partners of educational needs
Infrastructure Build Out
Implement Compass Training for current Staff
Implement Compass Training for new staff
Build Health Coach Training