| Month/Meeting(s) | Goals/Deliverables |
| --- | --- |
| SEPTEMBER 2021 |  |
| Commission Meeting Thursday, September 9, 2021 | DELIVERABLE: - Monthly quality update |
| PMWG Meeting Wed, Sep 15, 2021 | - Total Cost of Care (TCOC) Model update and SIHIS goals Updates - Focus on disparities - Work Plan review for FY 2024 & beyond - QBR RY 2024 Redesign updates policy discussion - HCAHPS Linear scoring addition/upfront investment - 30 day mortality development - Follow-up after discharge - Medicare update - Addition of Medicaid and behavioral health - THA TKA measure expansion options - ED 2-b wait time measure- eCQM version; HSCRC digital measures infrastructure development update - CDC measure under development- hospital onset bacteremia (HOB) - Reward/penalty cut-point discussion - Draft recommendations - MHAC - Trends in performance by PPCs…payment vs monitoring - Palliative care analysis- definition updates? (It is unclear when PC is POA) - RY 2024 methodology specifics - Grouper: Industry feedback - Model scores - COVID Updates - Other topics and public comment |
| OCTOBER 2021 |  |
| Commission Meeting Wed, Oct 13, 2021 | DELIVERABLES - Monthly quality update - QBR RY 2024 DRAFT recommendation |
| PMWG Meeting Wed, Oct 20, 2021 | - QBR RY 2024 FINAL recommendation- policy discussion - MHAC RY 2024 updates- policy discussion - RRIP - RY 2023 updates - RY 2024 policy - EDAC measure updates - Within-hospital disparities updates; PAI updates - Readmissions during COVID - Digital measures infrastructure overview-CRISP/Contractor (tentative) - CMS quality programs exemption update - Maximum Guardrail Report |
| NOVEMBER 2021 |  |
| Commission Meeting Thur, Nov 10, 2021 | DELIVERABLES - Quality update - QBR RY 2024 FINAL policy recommendation - Maximum Guardrail Report |
| PMWG Meeting Wed, Nov 17, 2021 | - MHAC RY 2024 DRAFT recommendation discussion - SIHIS Goal on readmission disparities discussion - PAU RY 2023 avoidable ED measures update - Digital measures infrastructure overview-CRISP/Contractor (tentative) - HSCRC hospital quality strategic updates discussion - COVID analytics for RY 2023 |
| DECEMBER 2021 |  |
| Commission Meeting Wed, Dec 08, 2021 | DELIVERABLES - Monthly quality update - MHAC RY 2024 DRAFT policy recommendation |
| PMWG Meeting Wed, Dec 15, 2021 | - MHAC RY 2024 FINAL policy discussion - RRIP RY 2024 policy discussion, continued - Finalize SIHIS Goal on within hospital readmission disparities - COVID analytics for RY 2023 |
| JANUARY 2022 |  |
| Commission Meeting Jan 2022 | DELIVERABLES - Quality Update - MHAC 2024 FINAL policy recommendation |
| PMWG Meeting Wed, Jan 19, 2022 | - RRIP RY 2024 DRAFT Policy discussion - Outpatient quality measurement strategy - Analyses of place of service - COVID analytics for RY 2023 |
| FEBRUARY 2022 |  |
| Commission Meeting Feb 2022 | DELIVERABLES - Monthly Quality Update - RRIP RY 2024 DRAFT Recommendation |
| PMWG Meeting Wed, Feb 16, 2022 | - RRIP RY 2024 FINAL policy - Digital measures - Options for measure adoption - COVID analytics for RY 2023 |
| MARCH 2022 |  |
| Commission Meeting March 2022 | - Monthly Quality Update - RRIP RY 2024 FINAL Recommendation |
| PMWG Meeting Wed, Mar 16, 2022 | - Digital measures update- discussion - Outpatient quality measurement strategy |
| APRIL 2022 |  |
| Commission Meeting April 2022 | - Monthly Quality Update |
| PMWG Meeting Wed, Apr 20, 2022 | - Revenue at Risk for quality compared to the nation estimate - Outpatient measurement - Digital measures follow up |
| MAY 2022 |  |
| Commission Meeting May 2022 | DELIVERABLES - Monthly Quality Update - PAU Savings RY 2023 draft report (in draft Update Factor Policy) |
| PMWG Meeting Wed, May 18, 2022 | - Outpatient measurement - Digital measures follow up |

| JUNE 2022 |  |
| --- | --- |
| Commission Meeting June 2022 | DELIVERABLES - Monthly Quality Update - PAU Savings RY 2023 report (in final update Factor Policy) |
| PMWG Meeting Wed, June 15, 2022 | TBD |